## Slide 1: BRP Plan for automatisk balancering
2024 |  |  |  |  |  |  |  |  |  |  | 
Jan | Feb | Mar | Apr | Maj | Jun | Jul | Aug | Sep | Okt | Nov | Dec
1
2
Milestone | Milestone description | Date​
 | Redundant mechanism for bud submission in webportal | 01.05.2024
 | BRPs can start testing bids in 15 minutes resolution and complex bid attributes. | Medio maj 2024
 | Full parallel operation established with all BRPs submitting bids in 15 minutes resolution. | 01.09.2024
 | Start testing of Bid Availability Report (for both mFRR and aFRR) | 01.09.2024
 | Go-live of Bid Availability Report | 01.10.2024
 | Start testing of Health Check message and Activation Result message (ReserveAllocationResult). | 01.10.2024
 | Go-live of automatic balancing | 03.12.2024
3
1
5
2
4
3
4
5
6
6
0
0
Go-live