## 2023
2023 | Energinet Maintenance Plan 2023 |  | Requirement (Sum) | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | Maj |  |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Okt |  |  |  |  | Nov |  |  |  | Dec
Activity | Consequence | Responsible | Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 48 | 50 | 51 | 52
CS Egtved |  | DOH, JJO | 20
MAN-ES Yearly service on compressors | Consequence - None | DOH, JJO | 20 | bar: Sep 36 to Sep 39
CS Everdrup |  | OBI, ESJ | 21.9
Yearly maintenance on ESD / blow-down system | Consequence; Station shut down (no flow) | OBI, ESJ | 1 | Sep 39: 27
Compressor performance test unit 1 | Consequence; Station shut down (no flow) | OBI, ESJ | 0.3 | Maj 19: 10
Compressor performance test unit 2 | Consequence; Station shut down (no flow) | OBI, ESJ | 0.3 | Maj 21: 24
Compressor performance test unit 3 | Consequence; Station shut down (no flow) | OBI, ESJ | 0.3 | Jun 23: 7
Yearly maintenance on compressors - Siemens | Consequence; Back-up compressor unavailable | OBI, ESJ | 20 | bar: Sep 36 to Sep 39
L/V Landlines |  | JGJ, TJM, MSC, PFP | 79
Pigging (Frøslev-Egtved; "Fast-track") | Consequence - None | PFP | 8 | bar: Maj 18 to Maj 19
Pigging - 2022 plan (New contract w/subcontractor) | Consequence - None | PFP | 15 | bar: Jul 27 to Aug 35
Vestfunen Tie in | Possible reduction in capacity towards Eastern DK. Reduction will be determined in June '23. | EYG | 56 | bar: Jul 27 to Aug 35
Offshore pipeline |  | MES | 15
Pigging - 2023 plan (New contract w/subcontractor) | Consequence - None | PFP | 15 | bar: Sep 36 to Okt 44
Nybro EPII-terminal |  | MADMA, JJO | 3.3
E&I: UPS, ESD and Back Up diesel Generator | Consequence: EPII terminal shut down 8-9/5 (no flow) | JJO | 2 | bar: Maj 19
Integration of safety systems at Nybro etc. | Consequence: No flow | JJO | 1 | bar: Sep 36
Asphalt project | Consequence: TBD - 50% capacity reduction expected | JJO | 0.3 | bar: Sep 39
Gas Storage Denmark |  | SHY | 4.2
Condensation tank CP T8301 | Stenlille – limited withdrawal; Timing can be coordinated with operations | SHY | 3 | bar: Sep 39 to Okt 40; Nov 45 to Dec 52
Power 5 service and test of emergencyserver | Isolated operation at sub system level; Timing can be coordinated with operations | SHY | 0.3
Exchange of 24V UPS on all sub stations | Redundancy available; Timing can be coordinated with operations | SHY | 0.3
Upgrade of ESD-PLC SUB 9 + IRT 11 | Stenille shut down; Timing can be coordinated with operations | SHY | 0.3 | bar: Okt 40 to Okt 41
Upgrade of ESD-PLC SUB 6 | No withdrawal; Timing can be coordinated with operations | SHY | 0.3 | bar: Maj 21

## KÅRSTØ
Asset | Type of event | Start | End | unit | Technical capacity | Available capacity | Unavailable capacity | Reason
Kårstø | Other unavailability | 2023-04-10T06:00:00+0200 | 2023-04-17T06:00:00+0200 | mcm/d | 97.6 | 92.0 | 5.6 | Yearly maintenance
Kårstø | Other unavailability | 2023-04-23T06:00:00+0200 | 2023-05-01T06:00:00+0200 | mcm/d | 97.6 | 85.0 | 12.6 | Yearly maintenance
Kårstø | Other unavailability | 2023-05-01T06:00:00+0200 | 2023-05-10T06:00:00+0200 | mcm/d | 97.6 | 78.0 | 19.6 | Yearly maintenance
Kårstø | Other unavailability | 2023-05-14T06:00:00+0200 | 2023-05-27T06:00:00+0200 | mcm/d | 97.6 | 92.0 | 5.6 | Yearly maintenance
Kårstø | Other unavailability | 2023-06-06T06:00:00+0200 | 2023-06-08T06:00:00+0200 | mcm/d | 97.6 | 92.2 | 5.4 | Yearly maintenance
Kårstø | Other unavailability | 2023-08-28T06:00:00+0200 | 2023-09-08T06:00:00+0200 | mcm/d | 97.6 | 88.0 | 9.6 | Yearly maintenance
Kårstø | Other unavailability | 2023-09-08T06:00:00+0200 | 2023-09-15T06:00:00+0200 | mcm/d | 97.6 | 75.0 | 22.6 | Yearly maintenance
Kårstø | Other unavailability | 2023-09-15T06:00:00+0200 | 2023-09-17T06:00:00+0200 | mcm/d | 97.6 | 85.0 | 12.6 | Yearly maintenance
Kårstø | Other unavailability | 2023-09-17T06:00:00+0200 | 2023-09-24T06:00:00+0200 | mcm/d | 97.6 | 91.0 | 6.6 | Yearly maintenance
Kårstø | Other unavailability | 2023-09-27T06:00:00+0200 | 2023-09-28T06:00:00+0200 | mcm/d | 97.6 | 30.0 | 67.6 | Yearly ESD test
Kårstø | Other unavailability | 2024-04-01T06:00:00+0200 | 2024-04-10T06:00:00+0200 | mcm/d | 97.6 | 78.0 | 19.6 | Yearly maintenance
Kårstø | Other unavailability | 2024-04-14T06:00:00+0200 | 2024-04-23T06:00:00+0200 | mcm/d | 97.6 | 85.0 | 12.6 | Yearly maintenance
Kårstø | Other unavailability | 2024-04-28T06:00:00+0200 | 2024-05-04T06:00:00+0200 | mcm/d | 97.6 | 85.0 | 12.6 | Yearly maintenance
Kårstø | Other unavailability | 2024-05-05T06:00:00+0200 | 2024-05-08T06:00:00+0200 | mcm/d | 97.6 | 84.0 | 13.6 | Yearly maintenance
Kårstø | Other unavailability | 2024-05-12T06:00:00+0200 | 2024-05-15T06:00:00+0200 | mcm/d | 97.6 | 84.0 | 13.6 | Yearly maintenance
Kårstø | Other unavailability | 2024-05-20T06:00:00+0200 | 2024-05-28T06:00:00+0200 | mcm/d | 97.6 | 92.2 | 5.4 | Yearly maintenance
Kårstø | Other unavailability | 2024-05-29T06:00:00+0200 | 2024-06-06T06:00:00+0200 | mcm/d | 97.6 | 92.2 | 5.4 | Yearly maintenance
Kårstø | Other unavailability | 2024-06-09T06:00:00+0200 | 2024-06-17T06:00:00+0200 | mcm/d | 97.6 | 92.2 | 5.4 | Yearly maintenance
Kårstø | Other unavailability | 2024-08-30T06:00:00+0200 | 2024-09-20T06:00:00+0200 | mcm/d | 97.6 | 0.0 | 97.6 | Yearly maintenance